Agile Workshop

Creating the Project Plan and Sprint Backlog for the Group Project

Case study: Hospital Patient Referral, Treatment and Administration System (HPAS)   |   Group size: 4   |   Date: 14 September 2026

Owners used in this plan (cross-functional): 靳宗尧 · 叶泓利 · 麻嘉汶 · 刘稣博. Each member is First Owner and Second Owner across all pathways (referral, patient identity, booking, clinical treatment, communication, finance, security/reporting); ownership rotates so every member works on every pathway.

Part 1  Understand the Case Study

The group read the full case study before creating technical tasks. The answers below are the agreed record of that discussion.

1.1 Discussion record

| Workshop question | Group answer |
| --- | --- |
| What organisation or business context is described? | A specialist hospital service that manages patients from GP or hospital referral through consultation, diagnosis, treatment, follow-up and ongoing communication. It will introduce a Hospital Patient Administration System (HPAS) to support the pathway. |
| Who are the main stakeholders? | Patients; GPs and referring organisations; Medical Secretaries; Consultants and other clinicians; Outpatient Bookings; Treatment/Chemotherapy Bookings; Call Handling; Clinical Nurse Specialist team and admin support; Patient Pathway Coordinators; Finance; Administrative Management; hospital management; insurers/funders; external scheduling, correspondence, clinical and payment providers. |
| What is the main business process? | Referral intake and document check → consultant clinical review → new-patient booking and notification → consultation, consent and authorised treatment request → funding/payment gate → treatment booking and multi-cycle review → clinic letter and follow-up → enquiry handling, with cancel/DNA and refund paths. |
| What problem is the proposed system trying to solve? | Information currently moves through legacy systems, electronic forms, email, telephone, letters and manual records. The hospital cannot reliably monitor progress, identify delays or keep a complete audit trail, while still keeping clinical, administrative and financial duties separate. |
| What are the key business rules? | Secretaries must not accept/reject referrals clinically. A new-patient appointment may be booked only after an authorised consultant accepts. Unauthorised treatment requests must not be processed by admin. Card data must not be stored. Payment (or exemption/funding/arrangement) is required before confirming a chargeable appointment, except recorded urgent clinical override. Finance must not make clinical decisions; clinicians must not approve refunds unless they also hold financial authority. Informal treatment changes are invalid. Call handlers must not give clinical advice. Clinic letters: 7-day delay, 1-month manager, 3-month higher management. Follow-up must not be silently booked outside the requested window. Audit records are immutable for ordinary users. |
| What exceptions or alternative paths are described? | Missing documents; reject / request further information / redirect; urgent referral; no suitable slot; unanswered/wrong-number/reschedule contact; external service unavailable (pending, no duplicates); declined/duplicate/incomplete payment; PSP charged but confirmation lost (investigation, no auto-retry); urgent treatment without confirmed payment; refund after cancel/change; urgent safety postponement with later authorisation; cancel/decline/DNA; delayed clinic letters; system/external outage with later recording. |
| What external systems or organisations are involved? | Referring GPs/hospitals; external scheduling service; external correspondence service; external treatment, laboratory, imaging and scheduling services; Payment Service Provider; insurers/funding organisations; existing hospital systems. |
| What information must be captured, stored, transferred or validated? | Patient identity; referral and supporting documents; missing-item requests; consultant decision, reason and decision-maker; booking request (speciality, priority, timeframe, requirements); contact attempts and outcomes; consent and treatment request (type, start, cycles, reviews, resources); funding organisation, authorisation reference, amount and limits; payment status, transaction reference, date and amount (no full card data); refunds; treatment modifications; enquiry log; clinic-letter timestamps and recipients; reminder/escalation history; cancel/DNA events; immutable audit of significant actions. |

Assumptions made by the group

Where the case is incomplete, the group records the ambiguity, will consult Tutors where possible, and uses the following assumptions until they are overturned.

| ID | Ambiguity in the case | Group assumption (reversible) | Ask |
| --- | --- | --- | --- |
| A1 | Complete rules for enquiry urgency are not yet agreed. | Treat chest pain, breathing difficulty, severe bleeding, inability to attend treatment the same day, or a clinician-marked urgent flag as urgent and route immediately to the CNS team. All other enquiries use admin / finance / clinical routing. | Tutor / clinical |
| A2 | Working practices are inconsistent across teams. | The case text is the single source of truth in Sprint 1. Conflicts are logged on the backlog and are not implemented as a silent choice. | Group / Tutor |
| A3 | Patients’ communication preferences may conflict with operational rules. | Store preferred channel and accessible format on the patient record. The two-week telephone rule remains mandatory. | Admin |
| A4 | The outage recording procedure is not specified. | Provide an offline activity log (time, actor, action, patient/referral). After recovery, an authorised user enters it marked recorded-after-outage. | Tutor |
| A5 | Cross-organisation patient matching is not specified. | Auto-link only on a unique match of NHS number (if present) + name + date of birth + postcode. Otherwise place in a manual matching queue. | Tutor |
| A6 | Implementation stack is not in the case, but the workshop examples use Camunda. | Model in BPMN, implement with Camunda forms and external workers, and mock all external services. | Tutor |
| A7 | Sprint length is not stated. | Three two-week sprints: S1 15–28 Sep 2026; S2 29 Sep–12 Oct 2026; S3 13–26 Oct 2026. | Tutor |
| A8 | Estimate unit is not stated. | Product backlog uses story points (1/2/3/5/8). Tasks use hours. Team velocity target is 45–50 SP per sprint. | Group |

Part 2  The First Two Days (14-15 Sep 2026)

Two-day scope (14-15 Sep 2026). Day 1 — case-study understanding, assumptions and sprint planning (T01, T02, T03, T60 done). Day 2 — start of Sprint 1 modelling: main BPMN and exception branches (T04, T05), referral form (T06), scheduling mock (T20), urgent path (T24), permission-matrix draft (T65) and the evidence folder (T72).

| Sprint | Task ID | Task Description | First Owner | Second Owner | Est. | Acceptance Conditions | Evidence | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | T01 | Draft case-study summary | 靳宗尧 | 麻嘉汶 | 3h | Eight discussion questions answered | This document Part 1 | Done |
| 1 | T02 | Assumptions A1–A8 | 靳宗尧 | 麻嘉汶 | 2h | Each ambiguity has an assumption | Assumption table | Done |
| 1 | T03 | Participants and lanes | 叶泓利 | 刘稣博 | 2h | Every role mapped | Participant table | Done |
| 1 | T60 | Goal-conflict page | 靳宗尧 | 麻嘉汶 | 3h | Burden vs accountability included | Conflict table | Done |
| 1 | T04 | Main BPMN referral to booking request | 靳宗尧 | 麻嘉汶 | 4h | No booking before accept | BPMN v0.9 | To Do |
| 1 | T05 | Exception branches on the referral | 靳宗尧 | 麻嘉汶 | 3h | Four decisions recorded | BPMN exceptions | To Do |
| 1 | T06 | Referral form and document checks | 叶泓利 | 刘稣博 | 3h | Incomplete cannot be complete | Field list / form | To Do |
| 1 | T20 | Scheduling mock (success / no-slot / timeout) | 叶泓利 | 刘稣博 | 4h | Three responses switchable | Mock | To Do |
| 1 | T24 | Urgent path and no-slot escalation | 麻嘉汶 | 靳宗尧 | 3h | Out-of-window confirm fails | Negative test | To Do |
| 1 | T65 | Role-permission matrix draft | 靳宗尧 | 麻嘉汶 | 3h | Every case role listed | rbac-matrix | To Do |
| 1 | T72 | Evidence folder for Sprint 1 | 刘稣博 | 叶泓利 | 1h | Folder exists; Done needs evidence | Directory | To Do |

Part 3  Stand-up 1 (14 Sep 2026)

Each member is ready to give an individual update: what I completed, what I will do next, what is blocking me, what evidence supports the update, whether I need second-owner support, and whether any handover is required. Group rule: a Completed item with no Evidence is treated as not done. The Second Owner must review before a task is marked Done.

Stand-up 1 — after planning (14 Sep 2026)

| Student | Completed Work | Evidence | Next Action | Blocker | Support Needed | Handover Required |
| --- | --- | --- | --- | --- | --- | --- |
| 靳宗尧 | Case-study summary, business rules R1–R22, assumptions A1–A8, participant-to-lane map. | This document Parts 1 and 2; T01–T03 Done. | Draft referral-main.bpmn (T04) and the four exception branches (T05). | Tutor has not yet confirmed enquiry-urgency rules; using A1 for now. | 刘稣博: walk through lanes for any missing role before BPMN freeze. | No |
| 叶泓利 | Reviewed booking, notification, no-slot and cancel/DNA rules; agreed Second Owner on A’s lanes. | Part 1 exception list; T03 review notes. | Specify scheduling-mock contract (success / no-slot / timeout) so T20 can start. | Waiting for T04 field names for speciality, priority and timeframe. | 靳宗尧: JSON field contract by 18 Sep noon. | Yes — booking-request field contract from A to B |
| 麻嘉汶 | Extracted funding, payment, refund and clinical/finance separation rules R7–R12. | FR-08 to FR-12 in this document. | Draft funding three-state form fields and PSP mock behaviours for Sprint 2; review T07 with A so treatment-request fields include charge-relevant data. | None this week. Implementation starts Sprint 2. | 刘稣博: agree audit fields that must appear on every payment request. | No |
| 刘稣博 | Stakeholder conflict page (PB02); evidence-folder convention; initial RBAC concerns listed. | Conflict table; T60 Done. | Create /evidence/sprint1/{A,B,C,D} (T72) and draft the permission matrix (T65). | Camunda candidate-group names are not frozen. | Whole group: freeze role names at the 16 Sep meeting. | Yes — freeze of role names before T65/T66 |

Part 4  Decisions and Working Agreement

Decisions log

| Date | Decision | Made by | Revisit if |
| --- | --- | --- | --- |
| 14 Sep 2026 | Split work by pathway domain (clinical / booking / finance / cross-cutting), not by ‘modeller / coder / tester / slides’. | Group | Tutor requires a different team shape |
| 14 Sep 2026 | Three two-week sprints with the dates in A7. | Group | Taught calendar differs |
| 14 Sep 2026 | Camunda + BPMN + mocked external workers (A6). | Group | Module toolset is different |
| 14 Sep 2026 | Use A1 for enquiry urgency until Tutors issue rules. | Group | Tutor provides the real urgency policy |
| 14 Sep 2026 | No Done without evidence; Second Owner reviews first. | Group | Never — this is a working agreement |

Working agreement

Every backlog item and every task has a First Owner and a Second Owner.

Stand-up answers are individual. Review demonstrations are integrated.

External systems are mocked; the demo must still show pending, failure and no-duplicate behaviour.

Clinical, administrative and financial authorities are never collapsed into one role, even to ‘make the demo easier’.

End of group project plan. Source documents: Agile Workshop.docx; Case Study — Hospital Patient Referral, Treatment and Administration System.docx.