# Project Plan Evaluation

Subject: Hospital Patient Referral, Treatment and Administration System

## 1. Source basis and how "original / revised / actual" is read

- Requirement / expectation — the assignment brief Business_Process_Modelling_v3_0923_system.docx (what the system was asked to deliver: 7 stakeholder classes, the 8 sub-processes, dependency rules, and the five-phase BPM lifecycle).

- Plan — the consolidated Project and Test Plan and Decision Justification (v1.0, 29 Sep 2026): product backlog (PB-01…PB-15), sprint backlogs (S1–S4), acceptance test plan (AT-01…AT-21) and the design decisions.

- Actual progress — the same plan document's recorded Status columns, test results (TR-01…TR-07), acceptance results (AT-01…AT-21) and evidence table.

No separate "revised plan" draft was provided. Where the as-built model differs from the brief's expectation, that difference is reported as a scope/plan revision. Within the plan itself, status deltas (e.g. deferred timers/error events, a few evidence items marked Required) are the only visible revisions.

## 2. Executive summary

- Scope: delivered in full against the backlog — all 15 backlog items reached Complete / Passed / Implemented, and all 21 acceptance scenarios passed with recorded evidence.

- Priorities: consistent — 14 of 15 items are Must; the single Should item (PB-14 clinic letter) was also implemented, so no planned scope was dropped.

- Estimates: the most visible weakness — the plan is expressed only as four sprints with no effort, story-point or calendar estimate.

- Task allocation: faithful to the brief's responsibility boundaries; the 24 user tasks, 24 workers and 20 messages are pairwise consistent (TR-03/04/05 passed).

- Dependencies & integration: modelled with message flows and a single correlationKey; verified end-to-end (TR-02 passed).

- Risks: identified and controlled through documentation and operating procedures, but technical exception handling (Boundary/Timer/Error events) was deferred, which is the main residual risk.

- Sprint outcomes: all four sprints completed on plan with no spillover.

## 3. Dimension-by-dimension evaluation

| Dimension | Requirement (brief) | Planned (test plan) | Actual delivery | Critical finding |
| --- | --- | --- | --- | --- |
| Scope | Model the referral→treatment→clinic-letter pathway; 7 stakeholder classes; 8 sub-processes; dependency rules; 5-phase BPM lifecycle | 4 executable processes, 7 lanes, 24 user tasks, 24 form bindings, 24 worker types, 20 messages; backlog PB-01…PB-15 | All 15 backlog items Complete/Passed/Implemented; AT-01…AT-21 passed; TR-01…TR-07 passed | Scope met. The brief's "Analyse" and live "Monitor" phases are only partly realised — monitoring is delivered as automated test evidence rather than live KPI tracking. |
| Priorities | Emphasis on keeping clinical, administrative and financial responsibility boundaries distinct | Backlog priority column: 14 × Must, 1 × Should (PB-14) | PB-14 (Should) also implemented; no Must item dropped | Priorities were held throughout; nothing was de-scoped. |
| Estimates | Not specified | Four sprints (S1–S4) with item lists, but no effort, story-point or calendar estimates | Delivered across the four sprints as planned | Gap: no quantitative estimation exists, so schedule variance cannot be measured numerically. |
| Task allocation | 7-stakeholder responsibility table; boundaries between clinical, admin and finance | Lane/participant boundaries (Table 33) and task-type mapping — User/Service/Send tasks (Table 34) | 24 user tasks ↔ 24 forms; 24 workers ↔ 24 BPMN types; 20 messages ↔ 20 constants (all consistent) | Allocation matches plan; the External Payment & Funding Providers is correctly a separate participant, not a Hospital lane. |
| Dependencies | Nine-process dependency table (clinical review←referral, treatment←consent, booking←clearance, etc.) | Message-flow interactions (Table 36) and 13 business rules (BR-01…BR-13) with correlationKey | Message-name and correlation consistency verified (TR-05); dependency routes covered by AT tests | Dependencies are satisfied; no outstanding dependency failure. |
| Risks | Exception handling implied but not enumerated | Section 2.6/2.7 documents assumptions and 7 exception classes; explicitly no Boundary/Timer/Error events | No failed acceptance test and no active incident at submission (1.9) | Residual risk: technical failures rely on Camunda retries + manual procedures because timer/error events were deferred. |
| Integration | External service providers (scheduling, lab, imaging, payment) exchange reliable statuses | 20 messages / 21 message flows; publish-and-correlate pattern; integrated process test | Integrated execution test passed (TR-02); AT-01…AT-21 passed; deployment/worker evidence captured | Integration verified end-to-end. Minor inconsistency: PE-07/PE-08 are marked Required while E-07…E-10 are listed Existing. |
| Sprint outcomes | Not specified as sprints in the brief | Four sprints: S1 business analysis, S2 forms/rules/messages, S3 workers/verification, S4 integration/submission | S1–S3 items Complete (S2-04, S3-04 Passed); S4 all Passed | All sprints delivered on plan with no carry-over. |

## 4. Sprint outcomes in detail

| Sprint | Theme | Planned items | Deliverables | Status |
| --- | --- | --- | --- | --- |
| Sprint 1 | Business analysis & process structure | S1-01…S1-03 | Stakeholder & dependency analysis; BPMN collaboration (4 processes, 7 lanes); executable skeleton | All Complete |
| Sprint 2 | Forms, rules & messages | S2-01…S2-04 | 24 forms & bindings; 29 condition expressions; 20 messages / 21 flows; Boolean completeness fix | 3 Complete, S2-04 Passed |
| Sprint 3 | Workers & automated verification | S3-01…S3-04 | 24 JobWorker types; message publication & correlation; 11 structural tests; process execution test | 3 Complete, S3-04 Passed |
| Sprint 4 | Integration evidence & submission | S4-01…S4-04 | End-to-end tests; AT-01…AT-21 executed; deployment/Worker evidence; clean versioned package | All Passed |

## 5. Risks, assumptions and exception handling

| Risk / exception | Current behaviour | Required control | Status |
| --- | --- | --- | --- |
| External Worker failure | Retry or incident, no explicit boundary route | Bound retries, log error, assign operator; retry only idempotent work | Controlled by procedure |
| Message not received | Receiver waits / no new instance | Verify subscription & correlationKey before controlled republish | Controlled |
| Payment / funding timeout | No timer event modelled | Service deadline → notify Finance → manual review | Deferred (residual risk) |
| Invalid form variable | Gateway may default or raise incident | Required fields, controlled values, type-consistent data | Mitigated by validation |
| Repeated Worker execution | Retry may republish message | correlationKey + operation ID + idempotent updates | Controlled |
| Missing-information delay | Process waits without a timer | Reminder/escalation/closure deadlines | Deferred (residual risk) |
| Manual intervention | No explicit escalation subprocess | Document authorised correction, audit note, retry decision | Controlled by procedure |
| Technical exception model | No Boundary/Timer/Error events in BPMN | Documented controls; deferred until tested | Deferred (residual risk) |

Key assumptions carried (2.7): Camunda 8.9-compatible client; one correlationKey per pathway; auth outside the model; clinical/financial decisions by qualified users; external providers return one recognised result; final deployment includes BPMN + every referenced form.

## 6. Dependencies and integration

The model keeps Sequence Flow inside a participant and uses Message Flow across participants (Table 36). The Hospital process coordinates the shared pathway because clinical, administrative and financial work depends on a common referral state. Nine dependency rules from the brief are preserved and re-expressed as business rules BR-01…BR-13; each automated task type has exactly one matching Java Worker (TR-03) and each human task references one deployable form (TR-04). Acceptance scenarios AT-01…AT-21 exercise every dependency branch, and the integrated process test (TR-02) passed, so integration is demonstrated rather than merely claimed.

## 7. Critical findings and recommendations

- Estimation discipline is missing. The plan shows four sprints but no sizing. Adopt explicit effort or story-point estimates so future schedule variance can be measured.

- Technical exception handling is deferred. Boundary/Timer/Error events and the related timeout/escalation controls are documented but not yet modelled; this is the single largest residual risk and should be the first item of any revised plan.

- Monitoring is test-based, not live. The brief's "Monitor" phase is satisfied by automated verification evidence rather than runtime KPI tracking — acceptable for submission, but note it as a gap against the full BPM lifecycle.

- Evidence status is slightly inconsistent. PE-07/PE-08 read Required while E-07…E-10 read Existing; reconcile the evidence ledger before final audit.

- Scope was held, not cut. All Must items delivered and the lone Should item also implemented — a disciplined outcome worth stating explicitly in the evaluation.

## 8. Conclusion

Against the supplied artefacts, the project's plan matched its requirements and its actual progress matched its plan: scope, priorities, task allocation, dependencies, integration and sprint outcomes are all delivered and evidenced. The evaluation therefore converges on two recommendations for the revised plan — introduce quantitative estimates, and close the deferred technical exception-handling gap — while recording that the BPM "Analyse/Monitor" phases remain only partially realised.